## Budget and Timeline
Consultant:
Project Name: Santa Paula Branch Line Trail Master Plan and EIR/EIS Update
Agency Name: Ventura County Transportation Commission
Project Manager Name:
Project Manager Contact Info:
List each principle task and subtask, providing both the budget and timeline for each. Add or delete rows or columns as needed.
[6 empty] | 2023-24 |  |  |  | 2024-25 |  |  |  | 2025-26
Task # | Task Title | Consultant | Subconsultant 1 | Subconsultant 2 | Total Cost | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
1 | Project Management
1.1 | RESERVED FOR VCTC - RFP Procurement
1.2 | RESERVED FOR VCTC - Consultant Selection and Contract
1.3 | Project Development Team (PDT) Meetings
2 | Existing Analysis and Assessment
2.1 | Existing Conditions Analysis
2.2 | Existing Bicycle and Pedestrian Facilities Map
2.3 | Equity Data and Analysis
3 | Outreach and Engagement
3.1 | Technical Advisory Committee
3.2 | Citizens Advisory Commmittee
3.3 | Targeted Stakeholder Meetings
3.4 | Website, Social Media Page, and Surveys
3.5 | Community Workshop (Quarterly)
3.6 | Attend Community Events
4 | Conceptual Planning
4.1 | Identify Constraints and Opportunities
4.2 | Proposed Alternatives Development
4.3 | Develop concept-level programmatic cost estimates
4.4 | Alternative Evaluation
4.5 | Risk Register
4.6 | Identify Financial Needs
4.7 | Create an Implementation Strategy
5 | Plan Production and Approval
5.1 | Draft Plan
5.2 | Draft Final Plan
5.3 | Final Plan
5.4 | Resolution
6 | Project Definition
7 | Technical Studies
7.1 | Section 4(f) and 6(f)
7.2 | Human Environment Technical Studies
7.3 | Physical Environment Technical Studies
7.4 | Biological Environment Technical Studies
7.5 | Climate Change
8 | Draft EIR/EIS
8.1 | Alternatives
8.2 | Cumulative Impacts
8.3 | Determining Significance under CEQA/NEPA
8.4 | CEQA Environmental Checklist and MMRP
8.5 | Section 4(f) and 6(f) Evaluations
8.6 | Draft EIR/EIS
9 | Public Participation
9.1 | Public Outreach meetings
9.2 | Circulation to Reviewing Agencies
9.3 | Comments and Responding to Comments
10 | Final EIR/EIS
10.1 | Final EIR/EIS
10.2 | Supplemental Technical Study Updates
11 | Regulatory Process
11.1 | Findings and Statement of Overriding Conditions
11.2 | Permits: USACE, RWQCB, CDFW
11.3 | ROD/NOD
12 | RESERVED FOR VCTC - Administrative
13 | CONTINGENCY
| TOTAL | 0 | 0 | 0 | 0
*Please note all projects must be completed by November 30, 2025.